## Blad1
cr = Create |  | Sprint |  |  |  |  | Sprint |  |  |  |  | Sprint |  |  |  |  | Sprint
|  | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4
Activity | Prio | 2018-06-11 | 2018-06-12 | 2018-06-13 | 2018-06-14 | 2018-06-15 | 2018-06-18 | 2018-06-19 | 2018-06-20 | 2018-06-21 | 2018-06-22 | 2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29 | 2018-07-02 | 2018-07-03 | 2018-07-04 | 2018-07-05 | 2018-07-06
cr. Index view | CF | bar: 2018-06-11
cr. login View | CF | bar: 2018-06-11
cr. registration view | CF | bar: 2018-06-14
cr. overview of Items to book | CF | bar: 2018-06-11
cr. booking view | CF | bar: 2018-06-12
cr. confirmation of booking | CF | bar: 2018-06-12
cr. checkin view | CF | bar: 2018-06-12
cr. checkin confirmation | RF | bar: 2018-06-12
cr. checkout view | CF | bar: 2018-06-12
cr. checkout confirmation | RF | bar: 2018-06-12
cr. view of daily Arrivals/departures | CF | bar: 2018-06-12
cr. change booking page | CF | bar: 2018-06-12
cr. change booking confirmation | RF | bar: 2018-06-12
cr. change guest details view | CF | bar: 2018-06-13
cr. change guest details confirmation | RF | bar: 2018-06-13
cr. logout View | CF | bar: 2018-06-14
cr. code first classes | CF
cr. database | CF
Update all Views with ModelNames | CF
cr. registration method | CF
cr. log in method | CF
cr. logout method | CF
cr. booking method | CF
cr. check in method | CF
cr. check out method | CF
cr. modify booking method | CF
cr. modify guest details method | CF
cr. Printout view | RF
cr. Printout Controller | RF
cr. class for cabin | AF
cr. booking view for cabin | AF
cr. confirmation view for cabin | AF
cr. controller for cabin | AF
cr. class for canoe | AF
cr. booking view for canoe | AF
cr. confirmation view for canoe | AF
cr. controller for canoe | AF
cr. class for boat | AF
cr. booking view for boat | AF
cr. confirmation view for boat | AF
cr. controller for boat | AF
cr. class for outboard motor | AF
cr. booking view for outboard motor | AF
cr. confirmation view for outboard motor | AF
cr. controller for outboard motor | AF
cr. role Recepitonist | AF
bughunting
Note on B2: The following prios are availabe(in decending order): CF=Core Feature RF=Required Feature AF=Add On Feature