## Blad1
cr = Create |  | Sprint |  |  |  |  | Sprint |  |  |  |  | Sprint |  |  |  |  | Sprint |  |  |  |  | Sprint |  |  |  |  | Sprint |  |  |  |  | Sprint
|  | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7
Activity | Prio | 2018-06-11 | 2018-06-12 | 2018-06-13 | 2018-06-14 | 2018-06-15 | 2018-06-18 | 2018-06-19 | 2018-06-20 | 2018-06-21 | 2018-06-22 | 2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29 | 2018-07-02 | 2018-07-03 | 2018-07-04 | 2018-07-05 | 2018-07-06 | 2018-07-09 | 2018-07-10 | 2018-07-11 | 2018-07-12 | 2018-07-13 | 2018-07-30 | 2018-07-31 | 2018-08-01 | 2018-08-02 | 2018-08-03 | 2018-08-13 | 2018-08-14 | 2018-08-15 | 2018-08-16 | 2018-08-17
cr. Index view | CF | bar: 2018-06-11
cr. login View | CF | bar: 2018-06-11
cr. registration view | CF | bar: 2018-06-14
cr. overview of Items to book | CF | bar: 2018-06-11
cr. booking view | CF | bar: 2018-06-12
cr. confirmation of booking | CF | bar: 2018-06-12
cr. checkin view | CF | bar: 2018-06-12
cr. checkin confirmation | RF | bar: 2018-06-12
cr. checkout view | CF | bar: 2018-06-12
cr. checkout confirmation | RF | bar: 2018-06-12
cr. view of daily Arrivals/departures | CF | bar: 2018-06-12
cr. change booking page | CF | bar: 2018-06-12
cr. change booking confirmation | RF | bar: 2018-06-12
cr. change guest details view | CF | bar: 2018-06-13
cr. change guest details confirmation | RF | bar: 2018-06-13
cr. logout View | CF | bar: 2018-06-14
cr. code first classes | CF | bar: 2018-06-21
cr. database | CF | bar: 2018-06-21
Update all Views with ModelNames | CF | bar: 2018-06-27
cr. registration method | CF | bar: 2018-07-03
cr. log in method | CF | bar: 2018-06-29
cr. logout method | CF | bar: 2018-06-29
cr. booking method | CF | bar: 2018-06-29
cr. check in method | CF | bar: 2018-07-02
cr. check out method | CF | bar: 2018-07-02
cr. modify booking method | CF | bar: 2018-07-13
cr. modify guest details method | CF | bar: 2018-07-10
cr. Printout view | RF
cr. Printout Controller | RF
cr. class for cabin | AF
cr. booking view for cabin | AF
cr. confirmation view for cabin | AF
cr. controller for cabin | AF
cr. class for canoe | AF
cr. booking view for canoe | AF
cr. confirmation view for canoe | AF
cr. controller for canoe | AF
cr. class for boat | AF
cr. booking view for boat | AF
cr. confirmation view for boat | AF
cr. controller for boat | AF
cr. class for outboard motor | AF
cr. booking view for outboard motor | AF
cr. confirmation view for outboard motor | AF
cr. controller for outboard motor | AF
cr. role Recepitonist | AF | bar: 2018-08-15
bughunting | bar: 2018-07-30 to 2018-08-14